## Summary
Defect Count | Grand Total (Excluding Closed) | New / Open | WIP | Rejected | On Hold | Closed
| 24 | 7 | 10 | 4 | 3 | 7

## Data (hidden)
Severity | Count of Severity
Critical | 9
Low | 5
Medium | 6
Minor | 6
High | 5

## Sheet2 (hidden)
Lifecycle Phase | Count of Lifecycle Phase
QAT | 18
UAT | 10
Integration | 3

## Sheet1 (hidden)
Assigned To | Count of Assigned To
Sam | 1
Adam | 4
Alex | 3
Arya | 4
Harry | 1
John | 1
Melisa | 1
Olivia | 1
Petter | 1
Ravi | 1
Rickson | 3
Rose | 1
Stella | 4
Toby | 4
William | 1

## Defect Tracking Log
DEFECT TRACKING LOG
Defect ID | Defect Description | Steps to Reproduce Defect | Expected Result | Actual Result | Status | Defect Type | Lifecycle Phase | Priority | Severity | Assigned To | Created By | Date Created | ETA | Module | Tester's Comments | Developer's Comment
PROJ-101 | Unmask button at end of password field not working | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username qatuser01@demoshoppingportal.com in the username field 4. Enter the password “qatuser001” and it is display in masked mode 5. Click on the unmask button (eye icon at end of password field) | On click on the unmask button (eye icon), the password should display as plain text. | On click on the unmask button (eye icon), the screen is unresponsive and doesn’t unmask. | Open | Functional | QAT | High | Low | Sam | Hanha | 2019-01-12 | 5 hrs | Login Page
PROJ-102 | Forget password doesn't display user name and answer security question is not enabled | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username qatuser01@demoshoppingportal.com in the username field 4. Click on Forget Password link. 5. Forget Password link opens a new window/tab 6. In the new tab/window, the username is filled as default from login page 7. Answer security question button is enabled. | On Forget Password link, username should be displayed from login page and Answer Security Question button should be enabled. | On Forget Password link, username is displayed as empty and Answer Security Question button isn’t enabled. | Reject | Functional | QAT | Medium | Minor | Ravi | Ethen | 2019-02-02 | 4 hrs | Login Page
PROJ-103 | Filter window on Product Portal Page freezes for price range 50 to 1000 AUD selection. | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. On Production Portal Page, click on filter button 5. On the filter window, select the price range scale from 50 AUD to 1000 AUD 6. On Click on save button, filter window closes, and user see product portal page. | On click of save button, filter window should close, and control come back to Product Page. | On click of save button, filter window freezes and doesn’t close | Reject | Functional | QAT | Low | Medium | John | Spencer | 2019-03-12 | 10 hrs | Product Selection Page
PROJ-104 | Filter window on Product Portal Page doesn’t filter results on multiple brands | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. On Production Portal Page, click on filter button 5. On the filter window, select multiple brand (more than one brand) 6. On Click on save button | On click of save button, filter window should close, and Product Portal filter result on brand selected. | On click of save button, products are not filtered based on selected brands. | Open | Functional | QAT | Medium | Medium | Melisa | Alex | 2019-04-19 | 8 hrs | Product Selection Page
PROJ-105 | Filter window on Product Portal Page doesn’t sort results on relevance type | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. On Production Portal Page, click on sort button 5. On the sort window, select relevance type 6. On Click on save button. | On click of save button, sorting window should close, and Product Portal filter result on most relevance type | On click of save button, products are not filtered based on relevance type | New | Functional | QAT | Low | Medium | Petter | Rob | 2019-05-07 | 5 hrs | Product Selection Page
PROJ-106 | Portal Url doesn't work in VPN | Steps to reproduce: 1. Connect to VPN 2. Open the browser 3. Load the URL DemoShoppingPortal.qat.com.au | URL should load | URL doesn't load | Reject | System | QAT | High | Minor | Olivia | John | 2019-01-13 | 3 hrs | Protal Url
PROJ-107 | Filter window on Product Portal Page doesn't open in UAT | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. On Production Portal Page, click on filter button | On click of save button, filter window should open. | On click of save button, filter window doesn't open | Reject | Environment | Integration | High | Critical | Rose | Peter | 2019-01-22 | 2 hrs | Product Selection Page
PROJ-108 | Filter window on Product Portal Page doesn’t sort results on price low to high beyond 1000 AUD. | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. On Production Portal Page, click on sort button 5. On the sort window, select price low to high 6. On Click on save button | On click of save button, sorting window should close, and Product Portal filter result on low to high for all price range | On click of save button, products are not sorted based on price range low to high beyond 1000AUD | Open |  | Integration | Medium | High | Harry | Kavya | 30/02/2019 | 15 hrs | Product Selection Page
PROJ-109 | Error while adding product into the shopping cart | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Select an item from from the site 5. Try to add the item into the shopping cart | The item should get added to the cart | It is throwing error when trying to add an item into the cart | Open | Functional | Integration | Low | Minor | William | Rose | 2019-02-09 | 10 hrs | Shopping Cart Pop Up
PROJ-110 | Error message is wrong while adding product into the shopping cart | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Select an item from from the site 5. Try to add the item into the shopping cart 6. It will Pop up wrong error message | The error message should be as mentioned in the requirement | The error message is wrong | Closed | Cosmetic | QAT | Low | Critical | Toby | Williams | 2019-03-15 | 12 hrs | Shopping Cart Pop Up
PROJ-111 | The discounts are not getting added in the shopping cart | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Go to the cart 5. Click on the checkout button 6. enter the coupon code 7.Click on add button | The coupon code should be added and discount should be deducted from the original amount | The discount is not getting added | Open | Requirement | QAT | High | High | Adam | Cathlin | 2019-03-11 | 5 hrs | Shopping Cart Pop Up
PROJ-112 | Amex card is not accepted | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Go to the cart 5. Click on the checkout button 6.Go to payments 7.Try making the payment using Amex card | While doing payment it should accept Amex card | It is not accepting Amex card | Open | Requirement | QAT | Medium | Critical | Stella | Christine | 2019-04-25 | 7 hrs | Payment Page
PROJ-113 | In the card detail section, it is taking more than 16 digits | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Go to the cart 5. Click on the checkout button 6.Go to payments 7.Try making the payment and enter more than 16 digits while entering card details | It should not accept 16 digit in card details section | It is accepting more than 16 digits | WIP | Functional | UAT | Low | Low | Arya | Chrish | 2019-05-29 | 4 hrs | Payment Page
PROJ-114 | Paypal is not working in UAT | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Go to the cart 5. Click on the checkout button 6.Go to payments 7.Try making payment using Paypal | It should accept Paypal mode of payment in every environment | It not accepting Payal payment in UAT | WIP | Environment | UAT | Medium | Medium | Rickson | Peter | 2019-06-18 | 6 hrs | Payment Page
PROJ-115 | Item quantity is not getting accepted properly | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Select an item and enter it quantity | The entered quantity is getting entered correctly. | The entered quantity is wrongly displayed. | Closed |  | UAT | Low | Minor | Alex | Melinda | 2019-07-17 | 1 hrs | Shopping Cart Pop Up
PROJ-116 | Error message is wrong while adding product into the shopping cart | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Select an item from from the site 5. Try to add the item into the shopping cart 6. It will Pop up wrong error message | The error message should be as mentioned in the requirement | The error message is wrong | Closed | Cosmetic | QAT | Low | Critical | Toby | Williams | 2019-03-15 | 12 hrs | Shopping Cart Pop Up
PROJ-117 | The discounts are not getting added in the shopping cart | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Go to the cart 5. Click on the checkout button 6. enter the coupon code 7.Click on add button | The coupon code should be added and discount should be deducted from the original amount | The discount is not getting added | WIP | Requirement | QAT | High | High | Adam | Cathlin | 2019-03-11 | 5 hrs | Shopping Cart Pop Up
PROJ-118 | Amex card is not accepted | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Go to the cart 5. Click on the checkout button 6.Go to payments 7.Try making the payment using Amex card | While doing payment it should accept Amex card | It is not accepting Amex card | WIP | Requirement | QAT | Medium | Critical | Stella | Christine | 2019-04-25 | 7 hrs | Payment Page
PROJ-119 | In the card detail section, it is taking more than 16 digits | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Go to the cart 5. Click on the checkout button 6.Go to payments 7.Try making the payment and enter more than 16 digits while entering card details | It should not accept 16 digit in card details section | It is accepting more than 16 digits | WIP | Functional | UAT | Low | Low | Arya | Chrish | 2019-05-29 | 4 hrs | Payment Page
PROJ-120 | Paypal is not working in UAT | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Go to the cart 5. Click on the checkout button 6.Go to payments 7.Try making payment using Paypal | It should accept Paypal mode of payment in every environment | It not accepting Payal payment in UAT | WIP | Environment | UAT | Medium | Medium | Rickson | Peter | 2019-06-18 | 6 hrs | Payment Page
PROJ-121 | Item quantity is not getting accepted properly | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Select an item and enter it quantity | The entered quantity is getting entered correctly. | The entered quantity is wrongly displayed. | Closed |  | UAT | Low | Minor | Alex | Melinda | 2019-07-17 | 1 hrs | Shopping Cart Pop Up
PROJ-122 | Error message is wrong while adding product into the shopping cart | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Select an item from from the site 5. Try to add the item into the shopping cart 6. It will Pop up wrong error message | The error message should be as mentioned in the requirement | The error message is wrong | Closed | Cosmetic | QAT | Low | Critical | Toby | Williams | 2019-03-15 | 12 hrs | Shopping Cart Pop Up
PROJ-123 | The discounts are not getting added in the shopping cart | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Go to the cart 5. Click on the checkout button 6. enter the coupon code 7.Click on add button | The coupon code should be added and discount should be deducted from the original amount | The discount is not getting added | WIP | Requirement | QAT | High | High | Adam | Cathlin | 2019-03-11 | 5 hrs | Shopping Cart Pop Up
PROJ-124 | Amex card is not accepted | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Go to the cart 5. Click on the checkout button 6.Go to payments 7.Try making the payment using Amex card | While doing payment it should accept Amex card | It is not accepting Amex card | On Hold | Requirement | QAT | Medium | Critical | Stella | Christine | 2019-04-25 | 7 hrs | Payment Page
PROJ-125 | In the card detail section, it is taking more than 16 digits | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Go to the cart 5. Click on the checkout button 6.Go to payments 7.Try making the payment and enter more than 16 digits while entering card details | It should not accept 16 digit in card details section | It is accepting more than 16 digits | On Hold | Functional | UAT | Low | Low | Arya | Chrish | 2019-05-29 | 4 hrs | Payment Page
PROJ-126 | Paypal is not working in UAT | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Go to the cart 5. Click on the checkout button 6.Go to payments 7.Try making payment using Paypal | It should accept Paypal mode of payment in every environment | It not accepting Payal payment in UAT | On Hold | Environment | UAT | Medium | Medium | Rickson | Peter | 2019-06-18 | 6 hrs | Payment Page
PROJ-127 | Item quantity is not getting accepted properly | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Select an item and enter it quantity | The entered quantity is getting entered correctly. | The entered quantity is wrongly displayed. | Closed |  | UAT | Low | Minor | Alex | Melinda | 2019-07-17 | 1 hrs | Shopping Cart Pop Up
PROJ-128 | Error message is wrong while adding product into the shopping cart | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Select an item from from the site 5. Try to add the item into the shopping cart 6. It will Pop up wrong error message | The error message should be as mentioned in the requirement | The error message is wrong | Closed | Cosmetic | QAT | Low | Critical | Toby | Williams | 2019-03-15 | 12 hrs | Shopping Cart Pop Up
PROJ-129 | The discounts are not getting added in the shopping cart | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Go to the cart 5. Click on the checkout button 6. enter the coupon code 7.Click on add button | The coupon code should be added and discount should be deducted from the original amount | The discount is not getting added | WIP | Requirement | QAT | High | High | Adam | Cathlin | 2019-03-11 | 5 hrs | Shopping Cart Pop Up
PROJ-130 | Amex card is not accepted | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Go to the cart 5. Click on the checkout button 6.Go to payments 7.Try making the payment using Amex card | While doing payment it should accept Amex card | It is not accepting Amex card | WIP | Requirement | QAT | Medium | Critical | Stella | Christine | 2019-04-25 | 7 hrs | Payment Page
PROJ-131 | In the card detail section, it is taking more than 16 digits | Steps to reproduce: 1. Go to DemoShoppingPortal.qat.com.au 2. Click on ‘Sign-In’ link at the top right-hand on the portal banner. 3. Enter username and password 4. Go to the cart 5. Click on the checkout button 6.Go to payments 7.Try making the payment and enter more than 16 digits while entering card details | It should not accept 16 digit in card details section | It is accepting more than 16 digits | WIP | Functional | UAT | Low | Low | Arya | Chrish | 2019-05-29 | 4 hrs | Payment Page

## Reference Data
Reference Data for Drop Downs
Status | Priority | Severity
Open | High | Critical
Closed | Medium | High
On Hold | Low | Medium
Reject |  | Low
New |  | Minor
WIP
Fixed

## Document Versoning
Document Version History
Version # | Implemented By | Approved By | Revision Date | Approved Date | Reason | Remarks

## Instructions
Defect Tracking Log Instructions
Field | Description
Defect ID | Defect ID is the Unique identifier for a defect.
Defect Description | Description of the defect state its subsystem, area, or other part of the product in which the defect is obtained or which is affected by the defect.
Steps to reciprocate Defect | Step by step description of the defect to reproduce it and understand its cause and find the solution to fix it.
Expected Result | The result expected as per the requirement that when the functionality works correctly.
Actual Result | The result which is acquired by executing the test case for the functionality.
Status | It states the current status of the defect. Such as In Progress, Closed, Reviewed etc.
Defect Type | An area that categorize the issues by department, vendor or what type of problem it may be.
Lifecycle Phase | List the lifecycle this defect was raised for, It can be: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Severity | In Software Testing, Defect severity can be classified into four class: Critical: This class of defect specify complete closure of the process, nothing can proceed further. Major: This class of defect is highly severe defect and crashes the system. However, certain parts of the system remain functional. Medium: This class of defect causes some unwanted behaviour, but the system is still functional. Low: This class of defect won't cause any major break-down of the system.
Priority | The priority code indicates the impact of this defect on the project: H = High (extremely important, the project cannot be successful without this defect being resolved) M = Medium (important to project success, but a work around exists) L = Low (desirable, but with little effect to project success if the defect is not fixed)
Assigned To | The person to whom the particular defect is assigned.
Created By | The person who reported the defect and raised in the defect management tool.
Date Created | The date on which the defect is raised or created in the defect management tool.
Estimated time to fix | The estimation of time duration, it is going to take to fix the defect.
Module/Page Name | It depicts the Module during which the defect is found.
Tester's Comments | Tester's Comments regarding the defect.
Developer's Comment | Developer's Comments regarding the defect.