## Report
Test Report Daily Status
Test Cases # |  | 250 |  |  | Open Defects |  | 32 |  | Status Date | 2019-05-26
Executed # |  | 178 | Executed % | 71% | Critical / High |  | 21 |  | QA Start Date | 2019-05-12
Pending # |  | 72 | Pending % | 29% | Medium |  | 6 |  | QA End Date | 2019-05-29
On Hold # |  | 25 | On Hold % | 10% | Low/Trivial |  | 5 |  | Overall Status | Concern
Open Defects
ID | Description |  |  |  | Opened | Severity | Status | Assignee | Comments
BUG001 | Screen freezes when user submit the form. |  |  |  | 2019-05-12 | High | Open | Ankit
BUG010 | User experience slowness when login for the first time. |  |  |  | 2019-05-13 | High | Open | Ankit
BUG005 | System not calculating the bank fees correctly. |  |  |  | 2019-05-14 | Critical | Open | Ankit | Critical as it can reject a policy.
BUG006 | Service desk users cannot see their profile icon. |  |  |  | 2019-05-15 | Medium | Open | Ankit | Workaround available using search.
BUG007 | Customers cannot update their phone numbers. |  |  |  | 2019-05-16 | Critical | Open | Ankit | Critical as users cannot change contact details.
BUG011 | The systems incorrectly calculates the tax amount on summary. |  |  |  | 2019-05-17 | High | Open | Ankit | A display issue. Underlying data is correct.
BUG116 | The auto generated email template does not have the right subject. |  |  |  | 2019-05-18 | Medium | Closed | Ankit
BUG117 | Alignment issue for the form buttons |  |  |  | 2019-05-19 | Trivial | Open | Ankit
BUG118 | Screen freezes when user submit the form. |  |  |  | 2019-05-20 | High | Open | Ankit
BUG119 | User experience slowness when login for the first time. |  |  |  | 2019-05-21 | High | Closed | Ankit
BUG120 | System not calculating the bank fees correctly. |  |  |  | 2019-05-22 | Critical | Open | Ankit | Critical as it can reject a policy.
BUG121 | Screen freezes when user submit the form. |  |  |  | 2019-05-23 | High | Open | Ankit
BUG122 | User experience slowness when login for the first time. |  |  |  | 2019-05-24 | High | Open | Ankit
BUG123 | System not calculating the bank fees correctly. |  |  |  | 2019-05-25 | Critical | Open | Ankit | Critical as it can reject a policy.
BUG124 | Service desk users cannot see their profile icon. |  |  |  | 2019-05-26 | Medium | Open | Ankit | Workaround available using search.
BUG125 | Customers cannot update their phone numbers. |  |  |  | 2019-05-27 | Critical | Open | Ankit | Critical as users cannot change contact details.
BUG126 | The systems incorrectly calculates the tax amount on summary. |  |  |  | 2019-05-28 | High | Open | Ankit | A display issue. Underlying data is correct.
BUG127 | The auto generated email template does not have the right subject. |  |  |  | 2019-05-29 | Medium | Open | Ankit
BUG128 | Alignment issue for the form buttons |  |  |  | 2019-05-30 | Trivial | Open | Ankit
BUG129 | Screen freezes when user submit the form. |  |  |  | 2019-05-31 | Critical | Open | Ankit
BUG130 | User experience slowness when login for the first time. |  |  |  | 2019-06-01 | High | Open | Ankit
BUG131 | System not calculating the bank fees correctly. |  |  |  | 2019-06-02 | Critical | Open | Ankit | Critical as it can reject a policy.
BUG132 | Service desk users cannot see their profile icon. |  |  |  | 2019-06-03 | Low | Closed | Ankit | Workaround available using search.
BUG133 | Customers cannot update their phone numbers. |  |  |  | 2019-06-04 | Critical | Open | Ankit | Critical as users cannot change contact details.
BUG134 | The systems incorrectly calculates the tax amount on summary. |  |  |  | 2019-06-05 | High | Open | Ankit | A display issue. Underlying data is correct.
BUG135 | The auto generated email template does not have the right subject. |  |  |  | 2019-06-06 | Medium | Open | Ankit
BUG136 | Alignment issue for the form buttons |  |  |  | 2019-06-07 | Trivial | Open | Ankit
BUG137 | The systems incorrectly calculates the tax amount on summary. |  |  |  | 2019-06-08 | High | Open | Ankit | A display issue. Underlying data is correct.
BUG138 | The auto generated email template does not have the right subject. |  |  |  | 2019-06-09 | Medium | Open | Ankit
BUG139 | Alignment issue for the form buttons |  |  |  | 2019-06-10 | Trivial | Open | Ankit
BUG140 | Screen freezes when user submit the form. |  |  |  | 2019-06-11 | High | Open | Ankit
BUG141 | User experience slowness when login for the first time. |  |  |  | 2019-06-12 | High | Open | Ankit

## Ref Data
Overall | Severity | Status
On Track | Critical | Open
Concern | High | Closed
Delayed | Medium | Abandon
Low
Trivial