## Versions
Document Control History
Business Unit |  | Confidential
Owner |  | Ankit Gupta
Author |  | Ankit Gupta
Location |  | 1 Center St, New York, NY
Confidential Class |  | High
Project template Info |  | Test Report Weekly
Reviewer |  | NYC Project Manager
Approver |  | NYC Project Manager
Document Revision History
Date | Version |  | Description | Revised By
2020-02-05 | 1 |  | Initial Version | Ankit Gupta
2020-02-05 | 1.1 |  | Weeks Data Added | Ankit Gupta

## Weekly-Style1
Weekly QA Status Report - ECB Debt Collection Project
Key Highlights |  | QA Timeline
|  | Task | Start | Finish | Status | Owner | Comments
1 | Draft test plan has been sent on 02/05 to stakeholders for approval. | Draft Test Plan | 2020-02-05 | 2020-02-06 | Delayed | Ankit | Test plan sign off.
2 | QA environment issues have been raised with the integration team. | Create Test Cases | 2020-02-06 | 2020-02-07 | Concern | Ankit | Taking longer than expected.
3 | High number of defects observed due to Windows errors. | Create Integration Tests | 2020-02-07 | 2020-02-08 | On Track | Ankit
4 | Unplanned leave in the team has resulted in slower QA test runs. | Execute Tests Phase - 1 | 2020-02-08 | 2020-02-09 | On Track | Ankit
|  | Execute Tests Phase - 2 | 2020-02-09 | 2020-02-10 | On Track | Ankit
|  | Execute Integration Tests | 2020-02-10 | 2020-02-11 | Concern | Ankit | End date at risk with all the delays.
Test Execution Status |  | Defect Count |  |  | Risks and Issues
[5 empty] | Description |  |  | Owner
[5 empty] | Test plan does not include performance testing effort. |  |  | Ankit
[5 empty] | Environments are not fully stable due to software issues. |  |  | Ankit
[5 empty] | Testing effort is underestimated. |  |  | Ankit

## Week-Style2
Weekly Status Report
Project Name |  |  | NYC Department of Finance
Project ID |  |  | ECB Debt Collection
Application ID/Name |  |  | ECB CRM PORTAL
Start Report Date |  |  | 2020-02-05
End Report Date |  |  | 2020-02-10
Completed on (Milestone)
Project Manager |  |  | NYC Manager Name
QA Manager |  |  | NYC QA Manager Name
Functional Testing
Test Case ID | Description | Pass/Fail/Pending | Test Execution Date | Responsible Developer | Responsible Tester | Comment | Additional Comment other than QA team
TS101 | Reset Password in the login page | Pass | 2020-02-05 | Abhishek Gupta | Ankit Gupta | Working fine
Non-Functional Testing
Test Case ID | Description | Pass/Fail/Pending | Test Execution Date | Responsible Developer | Responsible Tester | Comment | Additional Comment other than QA team
Regression Testing
Test Case ID | Description | Pass/Fail/Pending | Test Execution Date | Responsible Developer | Responsible Tester | Comment | Additional Comment other than QA team

## Weekly-Style3
Weekly Status Report
Open Issues | Priority | Assigned To | Test Case ID | Reported Date | Status | Updated Date
| High |  |  |  | In Progress
| Low |  |  |  | Resolved
| Important |  |  |  | Unresolved
| Critical |  |  |  | Closed
Closed Issue | Test Case ID | Closure Date |  | Test Cases Summary
|  |  |  | Not Executed |  | 5
|  |  |  | Executed |  | 2
|  |  |  | Pass |  | 4
|  |  |  | Fail |  | 4
|  |  |  | Total Test Cases |  | 15
Upcoming Tasks |  |  |  | Coming Week Priorities
Project ID |  |  |  | Project
Total Test Cases remaining to cover
Scheduled Date |  |  |  | Scheduled Task
Reason for Extension |  |  |  | Date of Release
Defect Status | Bugs/Issues Summary
Defect Severity
|  | Critical | Medium | Low | Total | %
Closed
In Progress
Open
Pending
Total
%
Total No of Defects

## Data
Status | Test Execution |  | Severity
On Track | Total | 80 | Critical | 3
Delayed | Run | 54 | High | 10
Concern | Pending | 10 | Medium | 8
| On-Hold | 16 | Low | 3
| Pass | 34
| Fail | 20